## How to Use This Calendar
12-MONTH COMMUNICATIONS CALENDAR — HOW TO USE
PURPOSE
What this calendar does | Maps every planned lodge communication — emails, social posts, newsletter entries, roundtable reminders — to a specific date, audience, channel, and owner. The goal is to maintain a 6-weeks-ahead scheduling discipline so communications are proactive rather than reactive.
Who owns it | The Lodge Secretary maintains this calendar weekly. The Lodge Adviser audits it at each LEC meeting. Workstream leads (e.g., Social Media Lead) update their rows directly.
WEEKLY WORKFLOW
Step 1 — Friday review | Every Friday, the Secretary opens this sheet and scans the next 6 weeks. Any row without 'Scheduled' or 'Sent/Posted' status that is within 6 weeks needs immediate action.
Step 2 — LodgeMaster scheduling | Emails listed here should be scheduled in LodgeMaster at least 6 weeks before the send date. Mark 'Y' in the LodgeMaster Scheduled column when done.
Step 3 — Add new rows | Whenever a new event or communication is planned, add a row immediately. Don't wait — the calendar is only useful if it's complete.
Step 4 — LEC audit | Before each LEC meeting, sort by Status and review any 'Not Started' items due in the next 4 weeks. Escalate if an owner is stuck.
COLUMN GUIDE
Date | The date the communication should be SENT or POSTED (not drafted). Format: MM/DD/YYYY.
Month | Auto-populated. Used for filtering by month.
Audience | Who receives this communication. Use dropdown — one row per distinct audience segment.
Channel | Email / Facebook / Instagram / Roundtable / Newsletter / Text-Phone. Use dropdown.
Message Topic | Short description of what this communication covers. Include the subject line for emails.
Draft Owner | Name of the lodge member responsible for writing or scheduling this communication.
LodgeMaster Sched? | Y/N — has this been entered into LodgeMaster's advance-scheduling queue? (Emails only.)
Status | Not Started → In Draft → Scheduled → Sent/Posted. Update in real time.
Notes / Link | Any context: draft location, approval needed, template to use, link to Google Drive draft.
Priority | HIGH = tied to a deadline or major event. MEDIUM = important but flexible. LOW = nice to have.
TIPS
6-weeks-ahead rule | Gillian confirmed this discipline is working. The Secretary should never be scheduling a communication the week it goes out — that indicates the calendar wasn't maintained.
Pre-loading LEC reminders | Per the January 27 huddle: LEC meeting reminders at one week out and day-of should be pre-loaded for the entire program year in both this calendar AND LodgeMaster.
Pairing with the Social Media Guide | This calendar pairs with T11 (Social Media Content Calendar & Sync Guide). Facebook and Instagram posts listed here should be drafted and scheduled per T11's workflow.
Annual handoff | When the Secretary transitions, this file should be one of the first items in the handoff packet. The incoming Secretary inherits a working system, not a blank page.
CHANNEL COLOR KEY
Email (light blue) | Primary outreach channel. Schedule in LodgeMaster 6 weeks ahead.
Facebook (light green) | Lodge Facebook page. Requires council approval for new content types — see T11.
Instagram (light orange) | Lodge Instagram. Youth-led; follow T11 approval workflow.
Roundtable (light rose) | In-person update at district roundtable. Coordinate with T1 report.
Newsletter (light yellow) | Lodge newsletter (T13). Quarterly target aligned with council newsletter window.
Text/Phone (light lavender) | Direct outreach for urgent or personal communications.
Sequoyah Lodge · Workstream 3 · Communications · T10 · Prepared by Thrive Consulting Group · April 2026

## 12-Month Calendar
SEQUOYAH LODGE — 12-MONTH COMMUNICATIONS CALENDAR
Rolling 12-month calendar · Maintain 6 weeks ahead · Secretary updates weekly · Lodge Adviser audits at each LEC meeting
Date | Month | Audience | Channel | Message Topic / Subject | Draft Owner | LodgeMaster Scheduled? | Status | Notes / Link | Priority
▸ January 2026
01/05/2026 | January | All Members | Email | New Year welcome + 2026 program preview | Lodge Chief | Y | Sent / Posted | Includes 2026 lodge calendar attachment | HIGH
01/12/2026 | January | All Members | Email | Winter Banquet save-the-date | Secretary | Y | Sent / Posted | Schedule via LodgeMaster; flagship event | HIGH
01/16/2026 | January | All Members | Facebook | 2026 Lodge Officers introduction | Soc. Media Lead | N | Sent / Posted | Photos of new officers; tag chapters | MEDIUM
01/22/2026 | January | Chapter Chiefs | Email | January Chapter Chief check-in | Lodge Chief | N | Sent / Posted | Use T2 talking points; quarterly cadence | MEDIUM
01/29/2026 | January | Lodge Exec. Committee | Email | LEC Meeting Reminder (1 week out) | Secretary | N | Sent / Posted | Agenda attached; confirm attendance | HIGH
▸ February 2026
02/05/2026 | February | Lodge Exec. Committee | Email | LEC Meeting Reminder (day of) | Secretary | N | Sent / Posted | Include hybrid Zoom link | HIGH
02/12/2026 | February | All Members | Email | Spring Induction interest survey | Secretary | Y | Sent / Posted | Capture intent ahead of registration | HIGH
02/19/2026 | February | District Key 3 | Email | March roundtable coordination | Chapter Chiefs | N | Sent / Posted | Confirm OA presence with district chair | MEDIUM
02/22/2026 | February | All Members | Instagram | Throwback: 2025 Spring Induction highlights | Soc. Media Lead | N | Sent / Posted | 3–5 image carousel | LOW
02/26/2026 | February | All Members | Email | March events preview | Secretary | N | Sent / Posted | Camporee + callout ceremony details | MEDIUM
▸ March 2026
03/05/2026 | March | All Members | Email | Spring Camporee + callout ceremony preview | Lodge Chief | Y | Sent / Posted | Resume call-out at Spring Camporee (PMP priority) | HIGH
03/12/2026 | March | District Key 3 | Roundtable | OA update at district roundtables | Chapter Chiefs | N | Sent / Posted | Use T1 roundtable report; file copy with secretary | HIGH
03/19/2026 | March | Unit Leaders (Parents) | Email | Pre-Spring Induction parent letter | Secretary | N | Sent / Posted | Use T12 Pre-Ordeal Parent template | HIGH
03/26/2026 | March | Chapter Chiefs | Email | Election season check-in + chapter health | Lodge Chief | N | Sent / Posted | Prompt T3 monthly outreach checklist | MEDIUM
▸ April 2026
04/02/2026 | April | All Members | Email | Spring Camporee final logistics | Secretary | Y | Sent / Posted | Arrival, gear, schedule | HIGH
04/09/2026 | April | All Members | Facebook | Camporee callout ceremony recap + photos | Soc. Media Lead | N | Sent / Posted | Tag chapters represented | MEDIUM
04/16/2026 | April | All Members | Email | Spring Induction — registration closing | Secretary | Y | Sent / Posted | Final registration push | HIGH
04/23/2026 | April | Lodge Exec. Committee | Email | LEC Meeting Reminder (1 week out) | Secretary | N | Sent / Posted | Spring Induction debrief on agenda | HIGH
04/30/2026 | April | All Members | Email | May Ordeal Weekend logistics + Elangomat assignments | Secretary | Y | In Draft | Pair with T12 Pre-Ordeal parent letter | HIGH
▸ May 2026
05/01/2026 | May | All Members | Email | Ordeal Weekend Registration Reminder | Secretary | Y | Scheduled | Use LodgeMaster blast; attach event flyer | HIGH
05/08/2026 | May | Unit Leaders (Parents) | Email | Pre-Ordeal Parent Letter — Induction Candidate | Secretary | N | Not Started | See T12 template; customize bracketed fields | HIGH
05/10/2026 | May | All Members | Facebook | Countdown post: Ordeal Weekend in 3 weeks | Soc. Media Lead | N | Not Started | Photo from last ordeal; tag lodge page | MEDIUM
05/15/2026 | May | Chapter Chiefs | Email | Monthly Chapter Chief Check-In | Lodge Chief | N | Not Started | Use T2 talking points; prompt roundtable updates | MEDIUM
05/22/2026 | May | All Members | Instagram | Service project recap + photos | Soc. Media Lead | N | Not Started | 3–5 images; use approved lodge hashtag | LOW
05/31/2026 | May | All Members | Email | June events preview | Secretary | N | Not Started | Include LEC reminder for June 10 | MEDIUM
▸ June 2026
06/01/2026 | June | All Members | Email | Post-Ordeal Welcome — New Members | Secretary | N | Not Started | Use T12 Post-Ordeal template; Elangomat follow-up | HIGH
06/07/2026 | June | Lodge Exec. Committee | Email | LEC Meeting Reminder (1 week out) | Secretary | N | Not Started | Agenda attached; confirm attendance | HIGH
06/10/2026 | June | Lodge Exec. Committee | Email | LEC Meeting Reminder (day of) | Secretary | N | Not Started | Include Zoom link if hybrid | HIGH
06/14/2026 | June | All Members | Facebook | Ordeal recap + welcome new members | Soc. Media Lead | N | Not Started | Tag new members with permission | MEDIUM
06/20/2026 | June | District Key 3 | Email | Summer events outreach — partnership pitch | Chapter Chiefs | N | Not Started | Use T4 Event Partnership Pitch template | MEDIUM
06/28/2026 | June | All Members | Email | July–August events + calendar | Secretary | N | Not Started | Summer schedule preview; Brotherhood eligibility note | MEDIUM
▸ July 2026
07/03/2026 | July | All Members | Instagram | Independence Day / Brotherhood post | Soc. Media Lead | N | Not Started | OA service heritage angle | LOW
07/10/2026 | July | Chapter Chiefs | Email | Mid-year check-in + roundtable prep | Lodge Chief | N | Not Started | Prompt use of T3 outreach checklist | MEDIUM
07/17/2026 | July | All Members | Facebook | Fellowship weekend promo | Soc. Media Lead | N | Not Started | Registration link; share to BSA council page | HIGH
07/24/2026 | July | Unit Leaders (Parents) | Email | Brotherhood Eligibility Reminder | Secretary | N | Not Started | Use T12 Brotherhood Reminder template | HIGH
07/31/2026 | July | Lodge Exec. Committee | Email | LEC Meeting Reminder (1 week out) | Secretary | N | Not Started |  | HIGH
▸ August 2026
08/07/2026 | August | Lodge Exec. Committee | Email | LEC Meeting Reminder (day of) | Secretary | N | Not Started |  | HIGH
08/14/2026 | August | All Members | Email | Fall program year kickoff preview | Lodge Chief | N | Not Started | Chapter Officer Orientation Day save-the-date | HIGH
08/21/2026 | August | All Members | Facebook | Back to school / recruitment push | Soc. Media Lead | N | Not Started | Encourage units to schedule election visits | MEDIUM
08/28/2026 | August | Chapter Chiefs | Email | September roundtable prep — talking points | Brayden | N | Not Started | Link T2 talking points guide | MEDIUM
▸ September 2026
09/04/2026 | September | All Members | Email | September events + unit election window | Secretary | Y | Not Started | Schedule in LodgeMaster 6 weeks ahead | HIGH
09/11/2026 | September | District Key 3 | Roundtable | OA update at district roundtables | Chapter Chiefs | N | Not Started | Use T1 roundtable report; file copy with secretary | HIGH
09/18/2026 | September | All Members | Instagram | Chapter spotlight series launch | Soc. Media Lead | N | Not Started | One chapter per week; rotate through fall | MEDIUM
09/25/2026 | September | Lodge Exec. Committee | Email | LEC Meeting Reminder (1 week out) | Secretary | N | Not Started |  | HIGH
▸ October 2026
10/02/2026 | October | All Members | Email | Chapter Officer Orientation Day reminder | Secretary | Y | Not Started | TARGET EVENT: Oct 2026. See T8 facilitator guide | HIGH
10/09/2026 | October | All Members | Facebook | Orientation Day promo — register now | Soc. Media Lead | N | Not Started |  | HIGH
10/16/2026 | October | Chapter Chiefs | Email | LLD preparation — topic & presenter updates | Ethan | N | Not Started | Reference T6 planning guide timeline | HIGH
10/23/2026 | October | All Members | Email | November LLD save-the-date | Secretary | Y | Not Started | Schedule in LodgeMaster | HIGH
10/30/2026 | October | Lodge Exec. Committee | Email | LEC Meeting Reminder (1 week out) | Secretary | N | Not Started |  | HIGH
▸ November 2026
11/05/2026 | November | All Members | Email | LLD Conference reminder (final) | Secretary | Y | Not Started | LodgeMaster send; final headcount deadline | HIGH
11/08/2026 | November | All Members | Email | LLD Conference — day-of logistics | Secretary | N | Not Started | Location, arrival time, what to bring | HIGH
11/13/2026 | November | All Members | Email | Post-LLD recap + thank you | Lodge Chief | N | Not Started | Highlight T9 feedback themes; preview spring | MEDIUM
11/20/2026 | November | All Members | Newsletter | Q4 Lodge Newsletter (if relaunched) | Secretary | N | Not Started | See T13 newsletter template; semi-annual | LOW
11/27/2026 | November | Lodge Exec. Committee | Email | LEC Meeting Reminder (1 week out) | Secretary | N | Not Started |  | HIGH
▸ December 2026
12/04/2026 | December | All Members | Email | Year-end message from Lodge Chief | Lodge Chief | N | Not Started | Highlights + 2027 program year preview | HIGH
12/11/2026 | December | All Members | Facebook | Year-end photo collage / celebration post | Soc. Media Lead | N | Not Started | Member photos with permission; asset library | MEDIUM
12/18/2026 | December | Chapter Chiefs | Email | Officer transition prep — incoming chapter chiefs | Lodge Chief | N | Not Started | Election cycle reminder | HIGH
12/27/2026 | December | All Members | Email | New Year preview — January 2027 events | Secretary | N | Not Started | Keep brief; include registration links | MEDIUM

## Add New Communication
ADD A NEW COMMUNICATION
Fill out the fields below, then copy the completed row into the correct month on the 12-Month Calendar tab.
Date (MM/DD/YYYY)
Month
Audience
Channel
Message Topic / Subject
Draft Owner
LodgeMaster Scheduled? (Y/N)
Status | Not Started
Notes / Link
Priority